## Slide 1: Network Crashing

## Slide 2: Project Management with Certain Time Estimates
Summary of steps:
  Determine activities that need to be accomplished
  Determine precedence relationships and completion times
  Construct network diagram
  Determine the critical path
  Determine early start and late start schedules

## Slide 3: Project Management: Scheduling Projects with Certain Time Estimates
Create Network Diagram
  Based on order of precedence among activities

## Slide 4: Calculation of the Critical Path
Network approach helps calculate project duration
  A “path” is a sequence of activities that begins at the start of the project and goes to the end of the project
    1,2,3,5,6,7,8
    1,2,4,6,7,8
  The “critical path” is the path that takes the longest to complete
    and thus determines the minimum duration of the project
1
2
4
3
5
6
7
8

## Slide 5: Calculation of the Critical Path

## Slide 6: Calculation of the Critical Path
Critical Path
  The path that takes the longest to complete
1
2
4
3
5
6
7
8
4 weeks
10 weeks
4 weeks
2 weeks
3 weeks
16 weeks
4 weeks
1 week

## Slide 7: Calculation of the Critical Path
Critical Path
  The path that takes the longest to complete
1
2
4
3
5
6
7
8
4 weeks
10 weeks
4 weeks
2 weeks
3 weeks
16 weeks
4 weeks
1 week
C.P. = 40 weeks

## Slide 8: Calculation of the Critical Path
It is possible for multiple Critical Paths to exist
  New information suggests that Activity 4 will take 5 weeks instead of 4
1
2
4
3
5
6
7
8
4 weeks
10 weeks
4 weeks
2 weeks
3 weeks
16 weeks
4 weeks
1 week
X
5

## Slide 9: Calculation of the Critical Path
It is possible for multiple Critical Paths to exist
  New information suggests that Activity 4 will take 5 weeks instead of 4
1
2
4
3
5
6
7
8
4 weeks
10 weeks
5 weeks
2 weeks
3 weeks
16 weeks
4 weeks
1 week
X
5
C.P. = 40 weeks

## Slide 10: Calculation of the Critical Path
Critical Path may also shift if non-critical activity is lengthened or Critical Path activity is shortened
  Another update indicates it will actually take 6 weeks for Activity 4
1
2
4
3
5
6
7
8
4 weeks
10 weeks
4 weeks
2 weeks
3 weeks
16 weeks
4 weeks
1 week
X
6

## Slide 11: Calculation of the Critical Path
1
2
4
3
5
6
7
8
4 weeks
10 weeks
6 weeks
2 weeks
3 weeks
16 weeks
4 weeks
1 week
X
6
C.P. = 41 weeks
Critical Path may also shift if non-critical activity is lengthened or Critical Path activity is shortened
  Another update indicates it will actually take 6 weeks for Activity 4

## Slide 12: Determining Slack
Slack - The amount of time an activity on a non-critical path can be delayed without affecting the duration of the project (i.e., without putting it on the critical path)
  Uses four calculated values
    Early start - Earliest an activity can start (based on prerequisites)
    Early finish - Earliest it can finish (based on prerequisites & duration)
    Late start - Latest an activity can start and not delay the project
    Late finish - Latest an activity can finish and not delay the project

## Slide 13: Calculating Early Start (ES) and Early Finish (EF)
Move from left to right in network
  ES for 1st activity usually zero
  EF equals ES plus activity duration
  ES is latest of the EF times of an activity’s predecessors
THIS IS CALLED THE FORWARD PASS

## Slide 14: Calculating Late Start (LS) and Late Finish (LF)
Move from right to left in network
  LF for last activity equals EF for last activity
    Or target date if different
  LS equals LF minus activity duration
  LF is earliest of the LS times of an activity’s followers
THIS IS CALLED THE BACKWARD PASS

## Slide 15: Calculating Slack
Slack - The amount of time an activity on a non-critical path can be delayed without affecting the duration of the project (i.e., putting it on the critical path)
Computed by either:
Late Start - Early Start
or
Late Finish - Early Finish
Activities that have zero slack are, by definition, on the critical path

## Slide 16: Project Scheduling with Uncertain Time Estimates
Summary of steps:
  Determine activities that need to be accomplished
  Determine precedence relationships and completion times
  Construct network diagram
  Determine the critical path
  Determine early start and late start schedules
  Calculate the variances for the activity times
  Calculate the probability of completing by the desired due date

## Slide 17: Project Scheduling with Time Uncertainty
Take three time estimates
  Optimistic - What is the (realistic) fastest we can get an activity done?
  Pessimistic - What is the (realistic) worst case scenario for delay?
  Most likely - What is our “most likely” estimate?

## Slide 18: Project Scheduling with Time Uncertainty
Calculate the “expected time” for the activity
Where:
  Te = Expected Time
  o = Optimistic estimate
  m = Most likely estimate
  p = Worst-case (pessimistic) estimate

## Slide 19: Project Scheduling with Time Uncertainty
Activity #1
weeks
Activity #3
weeks
Activity #2
weeks

## Slide 20: Using Variation in Time Estimates to Assess Duration Probabilities
1
2
4
3
5
6
7
8
4 weeks
10 weeks
4.17 weeks
2.17 weeks
3 weeks
16.17 weeks
4.17 weeks
1.17 weeks
C.P. = 40.68 weeks
How do we interpret this estimate???
Probabilistically: 50% chance we will
finish faster, 50% chance
we will finish slower
Probability theory (“central limit theorem”) dictates that we assume that finish times across entire project are distributed “normally”

## Slide 21: Using Variation in Time Estimates to Access Duration Probabilities
Where:
Z = Number of standard deviations D is from Te
Te = Expected Time
D = Project duration I am thinking about
Note that this is , not 2 ,
We have to take the square root of the
“variance” to get the standard deviation

## Slide 22: Using Variation in Time Estimates to Access Duration Probabilities
We recognize that there is variation around our estimates
  We are estimating “most likely” or “expected” not “exact”
  Commonly assume a “Beta” distribution
    Another asymmetric distribution (because duration is never less than zero)
Calculating variance of the activity’s duration estimate:

## Slide 23: Using Variation in Time Estimates to Access Duration Probabilities
Activity #1
weeks
Activity #2
weeks
Activity #3
weeks

## Slide 24: Using Variation in Time Estimates to Assess Duration Probabilities
Calculate Critical Path using Te
Accumulate the variances of the individual activities
Apply formula to estimate project duration probabilities
Where:
Z = Number of standard deviations D is from Te
Te = Expected Time
D = Activity duration I am thinking about

## Slide 25: Using Variation in Time Estimates to Assess Duration Probabilities

## Slide 26: Using Variation in Time Estimates to Assess Duration Probabilities
1
2
4
3
5
6
7
8
4 weeks
10 weeks
4.17 weeks
2.17 weeks
3 weeks
16.17 weeks
4.17 weeks
1.17 weeks
What is the probability of finishing in 39 weeks or less?

## Slide 27: Using Variation in Time Estimates to Assess Duration Probabilities
1
2
4
3
5
6
7
8
4 weeks
10 weeks
4.17 weeks
2.17 weeks
3 weeks
16.17 weeks
4.17 weeks
1.17 weeks
Critical Path = 40.68 weeks
Sum of Variances = 2.56 weeks
What is the probability of finishing in 39 weeks or less?
Exhibit 8.22: Expected Values and Variances of Time Estimates

## Slide 28: Using Variation in Time Estimates to Assess Duration Probabilities
So, I look up the cumulative probability [G(z)] of the activity being completed before -1.05 standard deviations from the “most likely” estimate…
  … and find out I have a 85.314% chance of finishing within 39 weeks!! FROM APPENDIX A PAGE A3
Where:
Z = Number of standard deviations D is from Te
Te = Expected Time
D = Activity duration I am thinking about
1.6 = the square root of 2.56!!!
Standard deviation difference between “most likely” and desired duration

## Slide 29: Using Variation in Time Estimates to Access Duration Probabilities
So, what if I want to be 90 percent sure that I hit the project duration that I tell my boss I will (or she will fire me)?
  Reconfigure “Z” equation to solve for D
  Pick the value of “Z” that corresponds to the level of certainty I want (90% = +1.30)
  Solve
weeks!!!
What if I can stand to be only 80% sure??
Find probability under G(z) in Appendix B and translate to number of standard deviations

## Slide 30: Crashing Projects
A methodical approach to reducing project duration
  Focus on the time of activities on the critical path
  Looking for greatest improvement with least cost
    Additional labor, machinery
    Overtime and temporary employees
    Premiums paid to outside contractors for early delivery
Steps
  Create network
  Identify critical path
  Identify costs of reducing each activity on path
  Reduce most cost effective activity
  Look for critical path changes
    Beware of multiple critical paths
  Crash next activity

## Slide 31: Crashing Projects: Create the Network

## Slide 32: Crashing Projects: Identify the Critical Path
A
8
B
7
D
10
E
12
C
7
F
8
G
9
H
5
A-B-C-F-H
Critical Path = 35 days

## Slide 33
Crashing Projects: Identify Costs of Crashing Each Activity

## Slide 34: Crashing Projects: Reduce Most Cost Effective Activity
A
8
B
7
D
10
E
12
C
7
F
8
G
9
H
5
6
X

## Slide 35: Crashing Projects: Look for Critical Path Changes
A
8
B
7
D
10
E
12
C
7
F
8
G
9
H
5
Old Critical Path Completion = 35 days
Activity C Crashed by 1 day project completion = 34 days
Did that effect the critical path?
6
X

## Slide 36: Crashing Projects: Look for Critical Path Changes
A
8
B
7
D
10
E
12
C
7
F
8
G
9
H
5
Critical Path = 34 days
6
X
Multiple Critical Paths Appear!!!

## Slide 37
Crashing Projects: Crash Next Activity
Both C.P.
Path 1 Only
Path 2 Only
Exhibit 8.25: Crash Time and Costs

## Slide 38: Crashing Projects: Summary
Solution
Exhibit 8.26: Crashing Summary

## Slide 39: Caveats
Time estimates are frequently wrong
Early finishes are absorbed
Cushions get wasted
Resources aren’t always available when needed