## Slide 1: Lecture 15
CPM/PERT

## Slide 2: CPM/PERT
Critical Path Method (CPM)
  DuPont & Remington-Rand
  Deterministic task times
  Activity-on-node network construction
Project Evaluation and Review Technique (PERT)
  US Navy and Booz, Allen & Hamilton
  Probabilistic task time estimates
  Activity-on-arrow network construction

## Slide 3: Project Network
Activity-on-node (AON)
  nodes represent activities
  arrows show precedence relationships
Activity-on-arrow (AOA)
  arrows represent activities
  nodes are events for points in time
Event
  completion or beginning of an activity in a project
1
3
2
Branch
Node

## Slide 4: AOA Project Network for a House
3
2
0
1
3
1
1
1
1
2
4
6
7
3
5
Lay foundation
Design house and obtain financing
Order and receive materials
Dummy
Finish work
Select carpet
Select paint
Build house

## Slide 5: Concurrent Activities
Dummy
  two or more activities cannot share same start and end nodes
2
3
Lay foundation
Order material
(a) Incorrect precedence relationship
(b) Correct precedence relationship
3
4
2
Dummy
Lay
foundation
Order material
1
2
0

## Slide 6: Critical Path
Critical path
  Longest path through a network
  Minimum project completion time
A: 1-2-4-7 3 + 2 + 3 + 1 = 9 months
B: 1-2-5-6-7 3 + 2 + 1 + 1 + 1 = 8 months
C: 1-3-4-7 3 + 1 + 3 + 1 = 8 months
D: 1-3-5-6-7 3 + 1 + 1 + 1 + 1 = 7 months
1
3
2
2
4
3
3
1
5
1
6
1
7
1
Start

## Slide 7: Activity Start Times
1
3
2
2
4
3
3
1
5
1
6
1
7
1
Start
Start at 3 months
Start at 6 months
Start at 5 months
Finish at 9 months
Finish

## Slide 8: Node Configuration
1
0
3
3
0
3
Activity duration
Activity number
Earliest start
Latest start
Latest finish
Earliest finish

## Slide 9: Activity Scheduling
Earliest start time (ES)
  earliest time an activity can start
  ES = maximum EF of immediate predecessors
Forward pass
  starts at beginning of CPM/PERT network to determine earliest activity times
Earliest finish time (EF)
  earliest time an activity can finish
  earliest start time plus activity time
  EF= ES + t

## Slide 10: Earliest Activity Start and Finish Times
1
0
3
1
2
3
5
2
3
3
4
1
5
5
6
1
4
5
8
3
6
6
7
1
7
8
9
1
Start
Design house and obtain financing
Select paint
Lay foundation
Select carpet
Build house
Finish work
Order and receive materials

## Slide 11: Activity Scheduling
Latest start time (LS)
  Latest time an activity can start without delaying critical path time
  LS= LF - t
Latest finish time (LF)
  latest time an activity can be completed without delaying critical path time
  LF = minimum LS of immediate predecessors
Backward pass
  Determines latest activity times by starting at the end of CPM/PERT network and working forward

## Slide 12: Latest Activity Start and Finish Times
0
3
1
0
3
1
3
5
2
3
5
2
4
5
3
3
4
1
6
7
5
5
6
1
5
8
4
5
8
3
6
7
6
6
7
1
8
9
7
8
9
1
Start
Design house and obtain financing
Select paint
Lay foundation
Select carpet
Build house
Finish work
Order and receive materials

## Slide 13: Activity Slack
* Critical Path
0
9
9
8
8
*7
1
7
8
6
7
6
1
6
7
5
6
5
0
8
8
5
5
*4
1
4
5
3
4
3
0
5
5
3
3
*2
0
3
3
0
0
*1
Slack S
EF
LF
ES
LS
Activity

## Slide 14: Project Crashing
Crashing
  reducing project time by expending additional resources
Crash time
  an amount of time an activity is reduced
Crash cost
  cost of reducing activity time
Goal
  reduce project duration at minimum cost

## Slide 15: Time-Cost Relationship
Crashing costs increase as project duration decreases
Indirect costs increase as project duration increases
Reduce project length as long as crashing costs are less than indirect costs

## Slide 16: Time-Cost Tradeoff
Cost ($)
Project duration
Crashing Time
Minimum cost = optimal project time
Total project cost
Indirect cost
Direct cost