## Slide 1: Sources of Risk and Calculation of Risk Factor
Engr. Muhammad Zeeshan Ahad
M.Sc Construction Project Management (UK)
B.Sc Civil Engineering (Pakistan)
Affiliation
Royal Institute of Chartered Surveyors (U.K)
Pakistan Engineering Council (PAK)
Senior Lecturer Civil Engineering Deptt

## Slide 2: Sources of Risk
COMMERCIAL & STRATEGIC
COMPETITION
MARKET DEMAND LEVELS
GROWTH RATES
TECHNOLOGICAL CHANGE
STAKEHOLDER PERCEPTIONS
MARKET SHARE
PRIVATE SECTOR INVOLVEMENT
NEW PRODUCTS AND SERVICES
SITE ACQUISITION
ECONOMIC
DISCOUNT RATE
ECONOMIC GROWTH
ENERGY PRICES
EXCHANGE RATE VARIATION
INFLATION
DEMAND TRENDS
POPULATION GROWTH
COMMODITY PRICE

## Slide 3: Sources of Risk
CONTRACTUAL
CLIENT PROBLEMS
CONTRACTOR PROBLEMS
DELAYS
FORCE MAJEURE EVENTS
INSURANCE AND INDEMNITIES
JOINT VENTURE RELATIONS
FINANCIAL
DEBT/EQUITY RATIOS
FUNDING SOURCES
FINANCING COSTS
TAXATION IMPACTS
INTEREST RATES
INVESTMENT TERMS
OWNERSHIP
RESIDUAL RISKS FOR GOVERNMENT
UNDERWRITING

## Slide 4: Sources of Risk
ENVIRONMENTAL
AMENITY VALUES
APPROVAL PROCESSES
COMMUNITY CONSULTATION
SITE AVAILABILITY/ZONING
ENDANGERED SPECIES
CONSERVATION/HERITAGE
DEGRADATION OR CONTAMINATION
VISUAL INTRUSION
POLITICAL
PARLIAMENTARY SUPPORT
COMMUNITY SUPPORT
GOVERNMENT ENDORSEMENT
POLICY CHANGE
SOVEREIGN RISK
TAXATION

## Slide 5: Sources of Risk
SOCIAL
COMMUNITY EXPECTATIONS
PRESSURE GROUPS

## Slide 6: Sources of Risk
PROJECT INITIATION
ANALYSIS AND BRIEFING
FUNCTIONAL SPECIFICATIONS
PERFORMANCE OBJECTIVES
INNOVATION
EVALUATION PROGRAM
STAKEHOLDER ROLES AND RESPONSIBILITIES
PROCUREMENT PLANNING
INDUSTRY CAPABILITY
TECHNOLOGY AND OBSOLESCENCE
PRIVATE SECTOR INVOLVEMENT
REGULATIONS AND STANDARDS
UTILITY AND AUTHORITY APPROVALS
COMPLETION DEADLINES
COST ESTIMATION

## Slide 7: Sources of Risk
PROJECT DELIVERY STAGES
PROCUREMENT AND CONTRACTUAL
CONTRACT SELECTION
CLIENT COMMITMENT
CONSULTANT/CONTRACTOR PERFORMANCE
TENDERING
NEGLIGENCE OF PARTIES
DELAYS - WEATHER, INDUSTRIAL DISPUTES
DAMAGES AND CLAIMS
ERRORS IN DOCUMENTATION
FORCE MAJEURE EVENTS
INSURANCE AND INDEMNITIES

## Slide 8: Sources of Risk
CONSTRUCTION AND MAINTENANCE
BUILD ABILITY
CONTRACTOR CAPABILITY
DESIGN AND DOCUMENTATION
GEOTECHNICAL CONDITIONS
LATENT CONDITIONS
QUALITY CONTROLS
EQUIPMENT AVAILABILITY AND BREAKDOWNS
OBSOLESCENCE
INDUSTRIAL ACTION
MATERIALS AVAILABILITY
SHUT-DOWN AND START-UP
RECURRENT LIABILITIES
HEALTH AND SAFETY
ACCIDENT, INJURY
CONTAMINATION
NOISE DUST AND WASTE
DISEASE
IRRADIATION
EMISSIONS

## Slide 9: Sources of Risk
HUMAN FACTORS
ESTIMATION ERROR
OPERATOR ERROR
SABOTAGE
VANDALISM
NATURAL EVENTS
LANDSLIP/SUBSIDENCE
EARTHQUAKE
FIRE
FLOOD
LIGHTNING
WIND
WEATHER

## Slide 10: Sources of Risk
ORGANISATIONAL
INDUSTRIAL RELATIONS
RESOURCES SHORTAGE
SCHEDULING
OPERATIONAL POLICIES
MANAGEMENT CAPABILITIES
MANAGEMENT STRUCTURES
PERSONNEL SKILLS
WORK PRACTICES
SYSTEMS
COMMUNICATIONS OR NETWORK FAILURE
HARDWARE FAILURE
LINKAGES BETWEEN SUB-SYSTEMS
SOFTWARE FAILURE
POLICIES AND PROCEDURES

## Slide 11: Calculating Risk Factor
Two simple techniques are illustrated below for calculating risk factors. Both are essentially based on establishing quantitative criteria in reference to likelihoods and risk consequences.
The key objective is to create a means to nominally rank risks and identify the most significant.

## Slide 12: Example one
To estimate the likelihood of each risk arising and assess its impacts, initially use verbal scales that are readily understood. The tables show examples. Where necessary, adapt or adjust these to suit the circumstances, or use different scales for different criteria. Convert the verbal assessments to numerical measures.

## Slide 13: Example
Risk Likelihood | L | Risk Impact | I
Almost certain | 0.9 | Extreme | 0.9
Highly likely | 0.7 | Very high | 0.7
Likely | 0.3 | Medium | 0.3
Unlikely | 0.1 | Low | 0.1
Rare | 0.01 | Negligible | 0.01

## Slide 14: METHOD OF CALCULATING RISK
Calculate a ‘risk factor’ or combined risk measure for each major risk:
L = risk likelihood measure, on a scale 0 to 1
= average of likelihood factors;
I = impact measure, on a scale 0 to 1
= average of impact factors;
RF = risk factor
= L + I - (L x I)
The risk factor (RF), varies from 0 (low) to 1 (high). It reflects the likelihood of a risk arising and the severity of its impact.
The risk factor will be high if a risk is likely to occur, if its impacts are large, or both.

## Slide 15: RISK FACTOR PROFILE
Rank components or work packages in decreasing order of their risk factors, to generate a risk profile.
The ranking and the risk factors are used to decide which risks are acceptable and unacceptable, and to enable Risk Management priorities to be set.

## Slide 16: EXAMPLE TWO
This technique uses different quantitative values for likelihoods and consequences and derives risk factor values by simple addition. However, the objective, namely to develop a ranking of risks, remains the same.
Risk Likelihood |  | Scale
Frequent | Likely to occur frequently (several times per year) | 1
Reasonably probable | Likely to occur several times in life of operation (once per year) | 0
Occasional | Likely to occur sometime in life of operation (once in 10 years) | -1
Remote | Unlikely but possible in life of operation (once per 100 years) | -2
Very unlikely | Very unlikely (might occur once per 1000 years) | -

## Slide 17: Example
Risk Impact | Damage | Scale
Catastrophic | › $ 10 million | 7
Critical | $ 1 million ‹ $ 10 million | 6
Major | $ 100,000 ‹ $ 1 million | 5
Minor | $ 10,000 ‹ $100,000 | 4
Negligible | ‹ $ 10,000 | 3

## Slide 18: CALCULATION
In this example, risk factors are calculated by adding the likelihood and impact scores, and risk priorities are assigned on the following score groupings:

## Slide 19: RISK PROFILE
Score | Ranking | Management action
[5], 6, 7, 8 | Major risk | Imperative to suppress risk to lower level
4, [5] | Medium risk | Corrective measures are required in a reasonable time frame
‹ 4 | Low risk | Corrective action where practicable
Risk priorities are then allocated as follow

## Slide 20: End of Session